## All Packed
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 0 ? Accounts & Infrastructure | SP0-01 | - Provision PostgreSQL 16 database (Neon / AWS RDS). - Provision MongoDB 7 Atlas cluster (production-tier with backups). - Provision Redis 7 instance (Upstash or self-hosted). - Provision S3 bucket (or R2) for media storage with CORS and lifecycle rules. - Create accounts: Vercel/Netlify, Render/Railway, n8n, Resend, Cloudinary. | Guna | To Do | P0 | sprint-0;infrastructure;accounts | 10 | Epic
Sprint 0 ? Repository & Local Setup | SP0-02 | - Scaffold mono-repo: `apps/server`, `apps/client`, `packages/{shared-types, shared-constants, shared-utils}`. - Initialize `package.json` scripts: `dev`, `build`, `test`, `migrate`, `seed`. - Configure Node.js version lock (`.nvmrc`, `engines` field). | Guna | To Do | P0 | sprint-0;setup;monorepo | 6 | Epic
Sprint 0 ? Database Drivers & ORM Setup | SP0-03 | - Install and configure Prisma ORM for PostgreSQL (migrations, client generation). - Install and configure Mongoose for MongoDB with connection pooling. - Install `ioredis` for Redis client with reconnection logic. - Install `@aws-sdk/client-s3` for S3 presigned URLs. | Guna | To Do | P0 | sprint-0;database;orm | 8 | Epic
Sprint 0 ? CI/CD & Environment Config | SP0-04 | - Document all required env vars by tier (PostgreSQL, MongoDB, Redis, S3 credentials). - Create `.env.example` and `.env.local` templates. - Configure GitHub Actions for backend tests + frontend build previews. - Test local `npm run dev` with all three databases connected. - All cloud accounts created and credentials secured in `.env.local`. - `npm run dev` connects to all three databases without errors (health checks log success). - `prisma migrate dev --preview-feature` runs successfully (scaffold baseline). - CI pipeline triggers on PR. - Team can clone, `npm install`, and `npm run dev` independently. | Guna | To Do | P0 | sprint-0;ci;env | 18 | Epic
Sprint 1 ? Schema Implementation | SP1-01 | - Migrate and create `users` table (id, email, password_hash, phone, account_status, email_verified, created_at, updated_at). - Create indexes: `idx_users_email` (UNIQUE, LOWER), `idx_users_active_status` (partial), `idx_users_phone` (partial). - Migrate and create `email_verifications` table (id, user_id, token_hash, new_email, used_at, expires_at). - Create index: `idx_ev_token` (partial, WHERE used_at IS NULL). - Migrate and create `password_reset_tokens` table (id, user_id, token_hash, used_at, expires_at, ip_address). - Create indexes: `idx_prt_token`, `idx_prt_user`, `idx_prt_expires`. - Migrate and create `refresh_tokens` table (id, user_id, token_hash, device_id, platform, ip_address, revoked_at, expires_at). - Create indexes: `idx_rt_token`, `idx_rt_user`, `idx_rt_expires`. - Migrate and create `channels` table (id, type, invite_link, display_name, created_at, updated_at, deleted_at). - Create index: `idx_channels_invite_link` (partial). - Migrate and create `channel_members` table (channel_id, user_id, role, muted, archived, joined_at, left_at). - Create indexes: `idx_cm_user_active`, `idx_cm_channel`. - Migrate and create `blocked_users` table (blocker_id, blocked_id, created_at). - Create index: `idx_blocked_by_user`. - Migrate and create `push_tokens` table (id, user_id, device_id, token, platform, created_at). - Create index: `idx_push_user`. - _(Optional for MVP)_ Migrate `one_time_prekeys` table for Signal Protocol E2EE (defer to Sprint 7+). | Guna | To Do | P0 | sprint-1;schema;implementation | 34 | Epic
Sprint 1 ? Auth Endpoint Implementation | SP1-02 | - Implement `POST /auth/signup` (validate email, hash password with bcrypt cost≥12, create user + verification token). - Implement `POST /auth/verify-email` (consume token, activate user, return 200). - Implement `POST /auth/login` (validate email/password, issue JWT access + refresh token). - Implement `POST /auth/refresh` (validate refresh token, rotate with new token, revoke old). - Implement `POST /auth/logout` (revoke refresh token + all devices option). - Implement `POST /auth/forgot-password` (generate token, send email via Resend — _defer email to Sprint 5_). - Implement `POST /auth/reset-password` (consume token, update password, revoke all refresh tokens). - Implement JWT middleware: `authenticate()` — verify access token, attach user to `req.user`. - Implement authorization middleware: `requireChannel(channelId)` — check membership in PostgreSQL. | Guna | To Do | P0 | sprint-1;auth;api | 18 | Epic
Sprint 1 ? Security & Testing | SP1-03 | - Input validation with Zod for all auth payloads (email format, password strength, token format). - Rate-limit auth endpoints (5 req/min per email, 20 req/min per IP for signup). - Implement `GET /health` endpoint (returns 200 + { db: "connected", redis: "connected", mongodb: "connected" }). - Implement `GET /auth/me` endpoint (returns current user profile). - Unit tests: password hashing, JWT encoding/decoding, token expiry. - Integration tests: signup → verify → login → refresh → logout flow. - Database cleanup: reset migrations between test runs. - User can sign up with valid email and receives verification email placeholder (log only, no Resend yet). - User verifies email and account transitions to `active` status. - User logs in and receives access token + refresh token (refresh token persisted in DB). - Access token decodes to valid `{ userId, iat, exp }` claims. - Refresh token rotates on request (old token revoked). - `GET /auth/me` returns user profile when authenticated. - Logout revokes refresh token (subsequent refresh fails 401). - All tests pass in CI. - `GET /health` returns 200 with all services green. | Guna | To Do | P0 | sprint-1;security;testing | 32 | Epic
Sprint 2 ? MongoDB Schema & Indexes | SP2-01 | - Seed test data: 2-3 channels with 200+ messages split across buckets. | Guna | To Do | P0 | sprint-2;mongodb;schema | 4 | Epic
Sprint 2 ? Redis Setup & Ephemeral State | SP2-02 | - Implement Redis key patterns: `presence:{uid}`, `session:{uid}`, `socket:{socket_id}`, `unread:{uid}:{cid}`, `typing:{cid}`, `seq:{cid}`, `msg:lock:{cid}`. (partial: presence/unread/typing/seq/lock implemented; session/socket keys pending) - `SADD session:{uid}` — track active socket IDs per user. - Implement Redis Pub/Sub channels: `chat:{cid}` (message events), `presence:{uid}` (online status). - Test: cold start sequence seeding, lock contention under concurrent writes, Lua script atomicity. (sequence/concurrency tests present; some tests pending) | Guna | To Do | P0 | sprint-2;redis;ephemeral | 8 | Epic
Sprint 2 ? Channel & Participant Endpoints (PostgreSQL) | SP2-03 | - Implement `GET /channels/{id}` (fetch channel metadata + member list). - Implement `PUT /channels/{id}` (rename, update group invite link). | Guna | To Do | P0 | sprint-2;postgres;channels | 4 | Epic
Sprint 2 ? Testing | SP2-04 | - Unit tests: bucket split logic (when message_count reaches 100, create new bucket). - Integration tests: insert 150 messages, verify split across 2 buckets with correct seq ranges. - Bucket auto-splits at 100 messages; new messages go to new bucket. - All tests pass; no race conditions under concurrent load. | Guna | To Do | P0 | sprint-2;testing | 8 | Epic
Sprint 3 ? Message Send (Critical Path) | SP3-01 |  | Guna | To Do | P1 | sprint-3;messaging;critical-path | 4 | Epic
Sprint 3 ? Message List & History (Cursor-Based Pagination) | SP3-02 |  | Guna | To Do | P1 | sprint-3;messaging;history | 4 | Epic
Sprint 3 ? Message Edit & Delete | SP3-03 |  | Guna | To Do | P1 | sprint-3;messaging;edit-delete | 4 | Epic
Sprint 3 ? Receipts & Reactions | SP3-04 |  | Guna | To Do | P1 | sprint-3;messaging;reactions | 4 | Epic
Sprint 3 ? Rate Limiting & Security | SP3-05 |  | Guna | To Do | P1 | sprint-3;security;rate-limit | 4 | Epic
Sprint 3 ? Testing | SP3-06 |  | Guna | To Do | P1 | sprint-3;testing | 4 | Epic
Sprint 4 ? Socket.IO Server Setup | SP4-01 |  | Guna | To Do | P1 | sprint-4;socketio;server | 4 | Epic
Sprint 4 ? Room Management | SP4-02 |  | Guna | To Do | P1 | sprint-4;socketio;rooms | 4 | Epic
Sprint 4 ? Presence & Online Status | SP4-03 |  | Guna | To Do | P1 | sprint-4;presence | 4 | Epic
Sprint 4 ? Typing Indicators | SP4-04 |  | Guna | To Do | P1 | sprint-4;typing | 4 | Epic
Sprint 4 ? Redis Pub/Sub Integration | SP4-05 |  | Guna | To Do | P1 | sprint-4;pubsub;redis | 4 | Epic
Sprint 4 ? Connection & Reconnection | SP4-06 |  | Guna | To Do | P1 | sprint-4;reconnection | 4 | Epic
Sprint 4 ? Testing & Monitoring | SP4-07 |  | Guna | To Do | P1 | sprint-4;testing;monitoring | 4 | Epic
Sprint 5 ? Auth UI & Flows | SP5-01 | - Implement `SignUpForm` component (email, password strength indicator, agree to ToS). - Implement `SignInForm` component (email, password, "forgot password" link). - Implement email verification flow: extract token from URL, call `POST /auth/verify-email`, show success/error. - Implement password reset flow: request email → send token → reset form → redirect to login. - Implement JWT + refresh token handling: store access token in memory, refresh token in httpOnly cookie. - Implement auth guard: redirect unauthenticated users to login. - Implement logout: clear tokens, redirect to login. | Guna | To Do | P1 | sprint-5;frontend;auth | 14 | Epic
Sprint 5 ? Channels & Conversations | SP5-02 | - Implement Channels list view: - Call `GET /channels` with React Query (polling every 30s for new unread). - Display channel name, last message, unread badge, last_seen timestamp. - Sort by last_message_at DESC. - Implement Create Channel modal (DM: select user, Group: name + select participants). - Implement channel search (Cmd/Ctrl+K palette or search input). - Implement "Pin channel" / "Archive channel" quick actions. - Implement member list sidebar: name, online status (from presence), mute toggle. | Guna | To Do | P1 | sprint-5;frontend;channels | 16 | Epic
Sprint 5 ? Chat UI & Message Display | SP5-03 | - Implement Message list component: - Display messages paginated (cursor-based, `before_seq`). - "Load earlier" button at top; infinite scroll at bottom. - Group messages by sender + timestamp (15min window). - Implement Message input box: - Text area with emoji picker, mention autocomplete (defer @mention tagging to Sprint 7+). - Send button (keyboard shortcut: Shift+Enter or Cmd+Enter). - Implement Message item: sender, avatar, timestamp, body, reactions row, reply-to indicator. - Implement message actions: edit (hover menu), delete, react, reply (defer threading to Sprint 7+). - Implement optimistic send: send message, add to list with "pending" state, update on ACK with seq + server_at. | Guna | To Do | P1 | sprint-5;frontend;chat | 20 | Epic
Sprint 5 ? Realtime Integration (Socket.IO Client) | SP5-04 | - Install `socket.io-client` and implement Socket context provider. - Implement `useSocket()` hook: connect on mount, join channel on route change, clean up on unmount. - Listen to events: `message.created`, `message.edited`, `message.deleted`, `receipt_updated`, `reaction_added`. - On `message.created`: add to list if from other user, or update optimistic placeholder if from self. - Implement reconnection with exponential backoff (1s, 2s, 4s, 8s, max 30s). - On reconnect: query server for missed messages (pass last known seq). - Implement presence indicators: subscribe to `presence:{channel_members}`, show online/offline status. | Guna | To Do | P1 | sprint-5;frontend;realtime | 14 | Epic
Sprint 5 ? Typing Indicators & Live Presence | SP5-05 | - Implement typing indicator: emit `typing_start` on first keystroke, `typing_stop` on blur/send. - Display typing users: "Ravi is typing..." above message input. - Implement presence list: sidebar shows "3 online, 5 away, 2 offline". - Implement "last seen" badge: e.g., "Saw message at 2:45 PM". | Guna | To Do | P1 | sprint-5;frontend;presence | 8 | Epic
Sprint 5 ? Data Caching & Sync | SP5-06 | - Use React Query for REST endpoints with background refetch intervals. - Configure React Query cache: 5 min stale time for channels, 10 min for message history. - Implement scroll-to-bottom on new message (unless user scrolled up). - Implement read receipt: mark messages as read when visible in viewport (Intersection Observer). | Guna | To Do | P1 | sprint-5;frontend;cache | 8 | Epic
Sprint 5 ? Navigation & Layout | SP5-07 | - Implement sidebar: channels list, create channel button, profile menu. - Implement top bar: channel name, member count, search icon, more menu (pin, archive, leave). - Implement responsive layout: mobile drawer for sidebar, hide on large screens. - Implement loading states and error boundaries on channel + message list. | Guna | To Do | P1 | sprint-5;frontend;layout | 8 | Epic
Sprint 5 ? Accessibility & Polish | SP5-08 | - Add keyboard navigation: Cmd/Ctrl+K for search, Tab through channels, Enter to send. - Add ARIA labels to interactive elements. - Implement dark mode toggle (localStorage, TailwindCSS dark class). - Implement toast notifications for errors (e.g., "Message failed to send"). | Guna | To Do | P1 | sprint-5;frontend;a11y | 8 | Epic
Sprint 5 ? Testing | SP5-09 | - Unit tests: optimistic send logic, receive message update, typing indicator state. - Integration tests: signup → join channel → send message → receive in real-time. - Visual regression tests (Chromatic or Percy) for key components. - User signs up, verifies email, logs in. - User opens a channel and sees message history with pagination. - User types a message and sends it (optimistic insert, then ACK). - User B (connected to same channel) sees the message appear in real-time. - Typing indicator shows "User A is typing..." for 5s then auto-clears. - Presence shows "3 online" when 3 users are in channel. - Edit/delete message: change persists across all clients in real-time. - React with emoji: reaction appears instantly, other clients see it in <500ms. - Client reconnects after network loss and catches up with missed messages. - n8n receives and processes webhooks (message tagging occurs). | Guna | To Do | P1 | sprint-5;testing | 26 | Epic
Sprint 6 ? S3 Media Upload (Server-Side) | SP6-01 | - Implement `POST /upload/presigned-url` (generate S3 presigned upload URL): - Accept media_type (image, video, audio, file), filename. - Generate S3 key: `media/{channel_id}/{date}/{message_id}/{filename}`. - Generate presigned URL with 60s expiry. - Return { url, key, expiry }. - Implement lifecycle rules: auto-delete unprocessed uploads after 24h. - Implement CORS on S3 bucket: allow PUT from frontend origin. | Guna | To Do | P1 | sprint-6;media;s3 | 14 | Epic
Sprint 6 ? Client Upload UI | SP6-02 | - Implement file picker in message input: click to select, or drag-drop. - On file select: - Call `POST /upload/presigned-url` to get signed URL. - PUT file directly to S3 (multipart for large files, progress callback). - Show upload progress bar (visually block send until complete). - On upload success: attach media to message payload, send message with media URLs. - Implement media preview: image thumbnail, video play button, audio player, file icon. - Implement attachment gallery: media messages tab in channel (use MongoDB `idx_channel_media` index). | Guna | To Do | P1 | sprint-6;media;frontend | 16 | Epic
Sprint 6 ? Email Integration (Transactional via Resend) | SP6-03 | - Configure Resend API key and sender email. - Implement email templates: welcome, email-verification, password-reset. - Update auth endpoints to call Resend: - `POST /auth/signup` → send welcome email. - `POST /auth/verify-email` → on click, send confirmation email. - `POST /auth/forgot-password` → send reset link email. - Implement email unsubscribe link (optional for MVP). | Guna | To Do | P1 | sprint-6;email;resend | 14 | Epic
Sprint 6 ? n8n Webhooks & Automations | SP6-04 | - Deploy n8n instance (or use cloud). - Implement server webhooks: `POST /webhooks/n8n/message-created`, `POST /webhooks/n8n/user-signed-up`. - Implement webhook enqueue (Redis queue or in-memory): ack 202 immediately, process async. - Implement webhook retry logic: exponential backoff, max 5 retries, dead-letter queue on failure. - Implement HMAC-SHA256 webhook signing: include `X-Signature` header, n8n verifies. - Create n8n flow: trigger on message webhook → extract sentiment (call OpenAI or Hugging Face API) → store tag in MongoDB message. - Create n8n flow: trigger on user signup → log to Google Sheets or Slack (optional). - Implement monitoring: log webhook events, latencies, failures. | Guna | To Do | P1 | sprint-6;webhooks;n8n | 16 | Epic
Sprint 6 ? Media Processing (Optional MVP+) | SP6-05 | - Install `sharp` for image optimization: resize, convert to WebP. - Implement async media job: after upload, create thumbnail (360w) and preview (1080w). - Store processed files in S3 with optimized CDN paths. - Update MongoDB message: store both original + thumbnail URLs. | Guna | To Do | P1 | sprint-6;media;processing | 8 | Epic
Sprint 6 ? Testing | SP6-06 | - Unit tests: presigned URL generation, S3 key formatting. - Integration tests: upload file to S3, attach to message, verify URL persists in MongoDB. - Email tests: verify Resend receives correct payload, simulate bounce/unsubscribe. - Webhook tests: send webhook to n8n, verify signature validation, retry on failure. - User selects image, sees upload progress, sends message with attachment. - Message displays image thumbnail with zoom-on-click preview. - Verification email sent to user on signup; user clicks link, account activates. - n8n receives webhook on new message; sentiment tag appears in message history. - Upload fails gracefully: user sees error toast, can retry. - Webhook fails: server logs error, retries with backoff, eventually succeeds. | Guna | To Do | P1 | sprint-6;testing | 20 | Epic
Sprint 7 ? Error Tracking & Observability | SP7-01 | - Integrate Sentry: install SDK, configure DSN, enable error capture on both backend + frontend. - Implement custom breadcrumbs: log socket events, API calls, database queries. - Implement performance monitoring: mark critical paths (send message, fetch history, auth). - Set up alerts: critical errors (5xx, auth failures, database connection loss). - Implement health check aggregator: `GET /health` returns { postgres, mongodb, redis } with latencies. - Add request/response logging middleware: log endpoint, status, latency, user_id. | Guna | To Do | P1 | sprint-7;observability;sentry | 12 | Epic
Sprint 7 ? Database & Connection Tuning | SP7-02 | - Tune Prisma connection pool: set min/max based on server threads (default 5/10). - Tune MongoDB connection pool: set maxPoolSize (default 100, monitor connection count). - Tune Redis connection backoff: implement exponential backoff for reconnects. - Implement connection timeout middleware: cancel slow queries after 10s (configurable). - Monitor: active connections, query latencies (P50, P95, P99). - Run load test: 100 concurrent users, measure DB connection saturation. | Guna | To Do | P1 | sprint-7;performance;database | 12 | Epic
Sprint 7 ? Cold-Start Mitigations | SP7-03 | - Implement scheduled ping jobs: hit `/health` every 5 min to keep Render container warm. - Implement connection keepalive: periodically query each database to prevent timeout. - Implement pre-warmed connection pools on server startup. - Measure and log cold-start latency on deploy. | Guna | To Do | P1 | sprint-7;performance;cold-start | 8 | Epic
Sprint 7 ? Security Hardening | SP7-04 | - Implement HMAC-SHA256 webhook signature verification on all n8n webhooks. - Implement signed S3 URLs with TTL (10 min for upload, 24h for download). - Implement rate-limit headers: return X-RateLimit-\* on all endpoints. - Implement input sanitization: SQL injection, XSS, command injection tests. - Implement CSRF protection (if needed for forms). - Implement ACL checks: verify user is channel member before responding with messages. - Enable HTTPS everywhere, enforce HSTS header. - Review all user inputs: validate length, type, format with Zod before DB insert. | Guna | To Do | P1 | sprint-7;security;hardening | 16 | Epic
Sprint 7 ? E2E & Load Testing | SP7-05 | - Create Playwright E2E test suite: signup → verify → login → create channel → send message → edit/delete → logout. - Create load test: 100 concurrent users, each sends 10 messages/min for 10 min. - Measure: response latencies, database query times, error rates, memory consumption. - Run load test against staging environment before launch. - Create smoke test: basic happy path (login → send → logout) runs before every deploy. | Guna | To Do | P1 | sprint-7;testing;e2e | 10 | Epic
Sprint 7 ? Monitoring & Alerts | SP7-06 | - Set up Upstash Redis dashboard monitoring: key count, memory, hit rates. - Set up MongoDB Atlas monitoring: connection count, query latency, storage. - Set up PostgreSQL monitoring: active connections, query cache hit ratio. - Set up alerts: database down, error rate >1%, response time P95 >1s, memory >80%. - Create runbook: escalation procedures, on-call contacts. | Guna | To Do | P1 | sprint-7;monitoring;alerts | 10 | Epic
Sprint 7 ? Testing | SP7-07 | - Unit tests: all middleware, utility functions, validators. - Integration tests: full flows (auth, send, edit, delete, reactions). - Security tests: attempt SQL injection, XSS, CSRF — all should fail gracefully. - Load tests: measure latency under 100, 500, 1000 concurrent users. - Errors are captured in Sentry with full stack traces + context. - Health check returns 200 with all services green. - Load test sustains 100 concurrent users with <500ms P95 latency. - Cold-start latency <2s (on first request after deploy). - All rate limits enforced; requests over limit get 429. - Signed webhook requests pass verification; tampered requests fail 401. - E2E test suite passes 100% on staging before deploy. | Guna | To Do | P1 | sprint-7;testing | 22 | Epic
Sprint 8 ? Staging Environment | SP8-01 | - Create staging environment: separate PostgreSQL, MongoDB, Redis, S3 buckets. - Copy production-like env vars to staging (except real API keys — use test credentials). - Deploy backend to staging (Render, Railway, or similar). - Deploy frontend to staging (Vercel, Netlify). - Configure staging domain: e.g., `staging.vibechat.dev`. - Enable SSL certificate for staging domain. | Guna | To Do | P1 | sprint-8;staging | 12 | Epic
Sprint 8 ? E2E Testing & QA | SP8-02 | - Run full E2E test suite on staging (Playwright, Cypress, or manual). - Test flows: signup → verify → login → create DM → send message → edit/delete → logout. - Test group flows: create group → add members → send message → see presence. - Test media: upload image → verify thumbnail shows → edit caption → delete. - Test realtime: 2 browsers, verify message appears in real-time. - Test presence: log out one user, verify offline in other user's presence list. - Test error scenarios: network failure, invalid token, rate limit exceeded. - QA sign-off: all test cases pass. | Guna | To Do | P1 | sprint-8;qa;e2e | 16 | Epic
Sprint 8 ? Performance & Load Testing (Staging) | SP8-03 | - Run load test on staging: 100 concurrent users, 10 msg/min for 30 min. - Verify: no errors, latencies stable, no DB connection leaks. - Verify: Sentry error rate <0.1%, no critical alerts. - Measure: cost per request (API, database, storage), estimate production cost. | Guna | To Do | P1 | sprint-8;performance;staging | 8 | Epic
Sprint 8 ? Security Review & Compliance | SP8-04 | - Security audit: OWASP Top 10 checklist. - Privacy: verify no PII in logs, Sentry, or cache. - Terms of Service: draft if needed (defer detailed legal review to post-launch). - Data retention: implement cleanup jobs (e.g., delete verified-but-unused accounts after 30 days). | Guna | To Do | P1 | sprint-8;security;compliance | 8 | Epic
Sprint 8 ? Launch Checklist | SP8-05 | - DNS: configure production domain, verify CNAME/A records. - SSL certificate: ensure valid, set auto-renewal. - Environment variables: all production secrets provisioned. - Database backups: enable automated daily backups + point-in-time recovery. - Monitoring & alerts: all dashboards, alerts, and runbooks ready. - Incident response: on-call schedule, escalation contact, communication channels. - Onboarding docs: README, setup guide, API docs (Swagger / Postman collection). - Announcement: prepare launch post, social media, beta user email. | Guna | To Do | P1 | sprint-8;launch | 16 | Epic
Sprint 8 ? Production Deployment | SP8-06 | - Deploy backend to production (same infra as staging, separate secrets). - Deploy frontend to production. - Run smoke test on production: verify `/health` returns 200, login works. - Monitor error rate & latencies for 1 hour post-deploy. - Monitor cost: verify spending matches estimates. - Announce launch: send email to beta testers, post on social media. | Guna | To Do | P1 | sprint-8;deployment;production | 12 | Epic
Sprint 8 ? Post-Launch Tasks & Deferred Backlog | SP8-07 | - Collect user feedback: in-app survey, Discord, email. - Monitor analytics: sign-ups, DAU, message volume, error rates. - Create deferred features backlog for Sprint 9+: - End-to-end encryption (E2EE): implement Signal Protocol with `one_time_prekeys`. - Full-text search: implement MongoDB Atlas Search on messages. - Message threading: replies group under parent message. - Voice/video calls: integrate Twilio or Daily.dev. - Read-only channels / announcements: admin-only send. - Group permissions: roles (admin, moderator, member) with ACL. - Custom emoji / emoji reactions: expand from 4 default emoji. - User mentions (@name) + notification: push notification when mentioned. - Message forwarding: send message to another channel. - Typing indicator improvements: show % similarity to avoid spam. - User profile: bio, avatar, status message. - Block / report user: harassment prevention. - Giphy / Tenor integration: GIF picker in message input. | Guna | To Do | P1 | sprint-8;post-launch;backlog | 32 | Epic
Sprint 8 ? Testing & Monitoring | SP8-08 | - Integration test: production smoke test (login → send → logout). - Monitoring: daily dashboard review, alert response SLA <15 min. - Staging passes all E2E tests (100% pass rate). - Load test on staging: 100 users, no errors, P95 <500ms. - Production deployment succeeds, smoke test passes. - Error rate <0.1%, latency P95 <500ms on production (1h post-deploy). - Launch announcement sent, beta users can sign up and use app. - Monitoring + alerts active, on-call rotation established. - Post-launch backlog documented and prioritized. | Guna | To Do | P1 | sprint-8;testing;monitoring | 18 | Epic

## Sprint 0
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 0 ? Accounts & Infrastructure | SP0-01 | - Provision PostgreSQL 16 database (Neon / AWS RDS). - Provision MongoDB 7 Atlas cluster (production-tier with backups). - Provision Redis 7 instance (Upstash or self-hosted). - Provision S3 bucket (or R2) for media storage with CORS and lifecycle rules. - Create accounts: Vercel/Netlify, Render/Railway, n8n, Resend, Cloudinary. | Guna | To Do | P0 | sprint-0;infrastructure;accounts | 10 | Epic
Sprint 0 ? Repository & Local Setup | SP0-02 | - Scaffold mono-repo: `apps/server`, `apps/client`, `packages/{shared-types, shared-constants, shared-utils}`. - Initialize `package.json` scripts: `dev`, `build`, `test`, `migrate`, `seed`. - Configure Node.js version lock (`.nvmrc`, `engines` field). | Guna | To Do | P0 | sprint-0;setup;monorepo | 6 | Epic
Sprint 0 ? Database Drivers & ORM Setup | SP0-03 | - Install and configure Prisma ORM for PostgreSQL (migrations, client generation). - Install and configure Mongoose for MongoDB with connection pooling. - Install `ioredis` for Redis client with reconnection logic. - Install `@aws-sdk/client-s3` for S3 presigned URLs. | Guna | To Do | P0 | sprint-0;database;orm | 8 | Epic
Sprint 0 ? CI/CD & Environment Config | SP0-04 | - Document all required env vars by tier (PostgreSQL, MongoDB, Redis, S3 credentials). - Create `.env.example` and `.env.local` templates. - Configure GitHub Actions for backend tests + frontend build previews. - Test local `npm run dev` with all three databases connected. - All cloud accounts created and credentials secured in `.env.local`. - `npm run dev` connects to all three databases without errors (health checks log success). - `prisma migrate dev --preview-feature` runs successfully (scaffold baseline). - CI pipeline triggers on PR. - Team can clone, `npm install`, and `npm run dev` independently. | Guna | To Do | P0 | sprint-0;ci;env | 18 | Epic

## Sprint 1
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 1 ? Schema Implementation | SP1-01 | - Migrate and create `users` table (id, email, password_hash, phone, account_status, email_verified, created_at, updated_at). - Create indexes: `idx_users_email` (UNIQUE, LOWER), `idx_users_active_status` (partial), `idx_users_phone` (partial). - Migrate and create `email_verifications` table (id, user_id, token_hash, new_email, used_at, expires_at). - Create index: `idx_ev_token` (partial, WHERE used_at IS NULL). - Migrate and create `password_reset_tokens` table (id, user_id, token_hash, used_at, expires_at, ip_address). - Create indexes: `idx_prt_token`, `idx_prt_user`, `idx_prt_expires`. - Migrate and create `refresh_tokens` table (id, user_id, token_hash, device_id, platform, ip_address, revoked_at, expires_at). - Create indexes: `idx_rt_token`, `idx_rt_user`, `idx_rt_expires`. - Migrate and create `channels` table (id, type, invite_link, display_name, created_at, updated_at, deleted_at). - Create index: `idx_channels_invite_link` (partial). - Migrate and create `channel_members` table (channel_id, user_id, role, muted, archived, joined_at, left_at). - Create indexes: `idx_cm_user_active`, `idx_cm_channel`. - Migrate and create `blocked_users` table (blocker_id, blocked_id, created_at). - Create index: `idx_blocked_by_user`. - Migrate and create `push_tokens` table (id, user_id, device_id, token, platform, created_at). - Create index: `idx_push_user`. - _(Optional for MVP)_ Migrate `one_time_prekeys` table for Signal Protocol E2EE (defer to Sprint 7+). | Guna | To Do | P0 | sprint-1;schema;implementation | 34 | Epic
Sprint 1 ? Auth Endpoint Implementation | SP1-02 | - Implement `POST /auth/signup` (validate email, hash password with bcrypt cost≥12, create user + verification token). - Implement `POST /auth/verify-email` (consume token, activate user, return 200). - Implement `POST /auth/login` (validate email/password, issue JWT access + refresh token). - Implement `POST /auth/refresh` (validate refresh token, rotate with new token, revoke old). - Implement `POST /auth/logout` (revoke refresh token + all devices option). - Implement `POST /auth/forgot-password` (generate token, send email via Resend — _defer email to Sprint 5_). - Implement `POST /auth/reset-password` (consume token, update password, revoke all refresh tokens). - Implement JWT middleware: `authenticate()` — verify access token, attach user to `req.user`. - Implement authorization middleware: `requireChannel(channelId)` — check membership in PostgreSQL. | Guna | To Do | P0 | sprint-1;auth;api | 18 | Epic
Sprint 1 ? Security & Testing | SP1-03 | - Input validation with Zod for all auth payloads (email format, password strength, token format). - Rate-limit auth endpoints (5 req/min per email, 20 req/min per IP for signup). - Implement `GET /health` endpoint (returns 200 + { db: "connected", redis: "connected", mongodb: "connected" }). - Implement `GET /auth/me` endpoint (returns current user profile). - Unit tests: password hashing, JWT encoding/decoding, token expiry. - Integration tests: signup → verify → login → refresh → logout flow. - Database cleanup: reset migrations between test runs. - User can sign up with valid email and receives verification email placeholder (log only, no Resend yet). - User verifies email and account transitions to `active` status. - User logs in and receives access token + refresh token (refresh token persisted in DB). - Access token decodes to valid `{ userId, iat, exp }` claims. - Refresh token rotates on request (old token revoked). - `GET /auth/me` returns user profile when authenticated. - Logout revokes refresh token (subsequent refresh fails 401). - All tests pass in CI. - `GET /health` returns 200 with all services green. | Guna | To Do | P0 | sprint-1;security;testing | 32 | Epic

## Sprint 2
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 2 ? MongoDB Schema & Indexes | SP2-01 | - Seed test data: 2-3 channels with 200+ messages split across buckets. | Guna | To Do | P0 | sprint-2;mongodb;schema | 4 | Epic
Sprint 2 ? Redis Setup & Ephemeral State | SP2-02 | - Implement Redis key patterns: `presence:{uid}`, `session:{uid}`, `socket:{socket_id}`, `unread:{uid}:{cid}`, `typing:{cid}`, `seq:{cid}`, `msg:lock:{cid}`. (partial: presence/unread/typing/seq/lock implemented; session/socket keys pending) - `SADD session:{uid}` — track active socket IDs per user. - Implement Redis Pub/Sub channels: `chat:{cid}` (message events), `presence:{uid}` (online status). - Test: cold start sequence seeding, lock contention under concurrent writes, Lua script atomicity. (sequence/concurrency tests present; some tests pending) | Guna | To Do | P0 | sprint-2;redis;ephemeral | 8 | Epic
Sprint 2 ? Channel & Participant Endpoints (PostgreSQL) | SP2-03 | - Implement `GET /channels/{id}` (fetch channel metadata + member list). - Implement `PUT /channels/{id}` (rename, update group invite link). | Guna | To Do | P0 | sprint-2;postgres;channels | 4 | Epic
Sprint 2 ? Testing | SP2-04 | - Unit tests: bucket split logic (when message_count reaches 100, create new bucket). - Integration tests: insert 150 messages, verify split across 2 buckets with correct seq ranges. - Bucket auto-splits at 100 messages; new messages go to new bucket. - All tests pass; no race conditions under concurrent load. | Guna | To Do | P0 | sprint-2;testing | 8 | Epic

## Sprint 3
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 3 ? Message Send (Critical Path) | SP3-01 |  | Guna | To Do | P1 | sprint-3;messaging;critical-path | 4 | Epic
Sprint 3 ? Message List & History (Cursor-Based Pagination) | SP3-02 |  | Guna | To Do | P1 | sprint-3;messaging;history | 4 | Epic
Sprint 3 ? Message Edit & Delete | SP3-03 |  | Guna | To Do | P1 | sprint-3;messaging;edit-delete | 4 | Epic
Sprint 3 ? Receipts & Reactions | SP3-04 |  | Guna | To Do | P1 | sprint-3;messaging;reactions | 4 | Epic
Sprint 3 ? Rate Limiting & Security | SP3-05 |  | Guna | To Do | P1 | sprint-3;security;rate-limit | 4 | Epic
Sprint 3 ? Testing | SP3-06 |  | Guna | To Do | P1 | sprint-3;testing | 4 | Epic

## Sprint 4
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 4 ? Socket.IO Server Setup | SP4-01 |  | Guna | To Do | P1 | sprint-4;socketio;server | 4 | Epic
Sprint 4 ? Room Management | SP4-02 |  | Guna | To Do | P1 | sprint-4;socketio;rooms | 4 | Epic
Sprint 4 ? Presence & Online Status | SP4-03 |  | Guna | To Do | P1 | sprint-4;presence | 4 | Epic
Sprint 4 ? Typing Indicators | SP4-04 |  | Guna | To Do | P1 | sprint-4;typing | 4 | Epic
Sprint 4 ? Redis Pub/Sub Integration | SP4-05 |  | Guna | To Do | P1 | sprint-4;pubsub;redis | 4 | Epic
Sprint 4 ? Connection & Reconnection | SP4-06 |  | Guna | To Do | P1 | sprint-4;reconnection | 4 | Epic
Sprint 4 ? Testing & Monitoring | SP4-07 |  | Guna | To Do | P1 | sprint-4;testing;monitoring | 4 | Epic

## Sprint 5
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 5 ? Auth UI & Flows | SP5-01 | - Implement `SignUpForm` component (email, password strength indicator, agree to ToS). - Implement `SignInForm` component (email, password, "forgot password" link). - Implement email verification flow: extract token from URL, call `POST /auth/verify-email`, show success/error. - Implement password reset flow: request email → send token → reset form → redirect to login. - Implement JWT + refresh token handling: store access token in memory, refresh token in httpOnly cookie. - Implement auth guard: redirect unauthenticated users to login. - Implement logout: clear tokens, redirect to login. | Guna | To Do | P1 | sprint-5;frontend;auth | 14 | Epic
Sprint 5 ? Channels & Conversations | SP5-02 | - Implement Channels list view: - Call `GET /channels` with React Query (polling every 30s for new unread). - Display channel name, last message, unread badge, last_seen timestamp. - Sort by last_message_at DESC. - Implement Create Channel modal (DM: select user, Group: name + select participants). - Implement channel search (Cmd/Ctrl+K palette or search input). - Implement "Pin channel" / "Archive channel" quick actions. - Implement member list sidebar: name, online status (from presence), mute toggle. | Guna | To Do | P1 | sprint-5;frontend;channels | 16 | Epic
Sprint 5 ? Chat UI & Message Display | SP5-03 | - Implement Message list component: - Display messages paginated (cursor-based, `before_seq`). - "Load earlier" button at top; infinite scroll at bottom. - Group messages by sender + timestamp (15min window). - Implement Message input box: - Text area with emoji picker, mention autocomplete (defer @mention tagging to Sprint 7+). - Send button (keyboard shortcut: Shift+Enter or Cmd+Enter). - Implement Message item: sender, avatar, timestamp, body, reactions row, reply-to indicator. - Implement message actions: edit (hover menu), delete, react, reply (defer threading to Sprint 7+). - Implement optimistic send: send message, add to list with "pending" state, update on ACK with seq + server_at. | Guna | To Do | P1 | sprint-5;frontend;chat | 20 | Epic
Sprint 5 ? Realtime Integration (Socket.IO Client) | SP5-04 | - Install `socket.io-client` and implement Socket context provider. - Implement `useSocket()` hook: connect on mount, join channel on route change, clean up on unmount. - Listen to events: `message.created`, `message.edited`, `message.deleted`, `receipt_updated`, `reaction_added`. - On `message.created`: add to list if from other user, or update optimistic placeholder if from self. - Implement reconnection with exponential backoff (1s, 2s, 4s, 8s, max 30s). - On reconnect: query server for missed messages (pass last known seq). - Implement presence indicators: subscribe to `presence:{channel_members}`, show online/offline status. | Guna | To Do | P1 | sprint-5;frontend;realtime | 14 | Epic
Sprint 5 ? Typing Indicators & Live Presence | SP5-05 | - Implement typing indicator: emit `typing_start` on first keystroke, `typing_stop` on blur/send. - Display typing users: "Ravi is typing..." above message input. - Implement presence list: sidebar shows "3 online, 5 away, 2 offline". - Implement "last seen" badge: e.g., "Saw message at 2:45 PM". | Guna | To Do | P1 | sprint-5;frontend;presence | 8 | Epic
Sprint 5 ? Data Caching & Sync | SP5-06 | - Use React Query for REST endpoints with background refetch intervals. - Configure React Query cache: 5 min stale time for channels, 10 min for message history. - Implement scroll-to-bottom on new message (unless user scrolled up). - Implement read receipt: mark messages as read when visible in viewport (Intersection Observer). | Guna | To Do | P1 | sprint-5;frontend;cache | 8 | Epic
Sprint 5 ? Navigation & Layout | SP5-07 | - Implement sidebar: channels list, create channel button, profile menu. - Implement top bar: channel name, member count, search icon, more menu (pin, archive, leave). - Implement responsive layout: mobile drawer for sidebar, hide on large screens. - Implement loading states and error boundaries on channel + message list. | Guna | To Do | P1 | sprint-5;frontend;layout | 8 | Epic
Sprint 5 ? Accessibility & Polish | SP5-08 | - Add keyboard navigation: Cmd/Ctrl+K for search, Tab through channels, Enter to send. - Add ARIA labels to interactive elements. - Implement dark mode toggle (localStorage, TailwindCSS dark class). - Implement toast notifications for errors (e.g., "Message failed to send"). | Guna | To Do | P1 | sprint-5;frontend;a11y | 8 | Epic
Sprint 5 ? Testing | SP5-09 | - Unit tests: optimistic send logic, receive message update, typing indicator state. - Integration tests: signup → join channel → send message → receive in real-time. - Visual regression tests (Chromatic or Percy) for key components. - User signs up, verifies email, logs in. - User opens a channel and sees message history with pagination. - User types a message and sends it (optimistic insert, then ACK). - User B (connected to same channel) sees the message appear in real-time. - Typing indicator shows "User A is typing..." for 5s then auto-clears. - Presence shows "3 online" when 3 users are in channel. - Edit/delete message: change persists across all clients in real-time. - React with emoji: reaction appears instantly, other clients see it in <500ms. - Client reconnects after network loss and catches up with missed messages. - n8n receives and processes webhooks (message tagging occurs). | Guna | To Do | P1 | sprint-5;testing | 26 | Epic

## Sprint 6
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 6 ? S3 Media Upload (Server-Side) | SP6-01 | - Implement `POST /upload/presigned-url` (generate S3 presigned upload URL): - Accept media_type (image, video, audio, file), filename. - Generate S3 key: `media/{channel_id}/{date}/{message_id}/{filename}`. - Generate presigned URL with 60s expiry. - Return { url, key, expiry }. - Implement lifecycle rules: auto-delete unprocessed uploads after 24h. - Implement CORS on S3 bucket: allow PUT from frontend origin. | Guna | To Do | P1 | sprint-6;media;s3 | 14 | Epic
Sprint 6 ? Client Upload UI | SP6-02 | - Implement file picker in message input: click to select, or drag-drop. - On file select: - Call `POST /upload/presigned-url` to get signed URL. - PUT file directly to S3 (multipart for large files, progress callback). - Show upload progress bar (visually block send until complete). - On upload success: attach media to message payload, send message with media URLs. - Implement media preview: image thumbnail, video play button, audio player, file icon. - Implement attachment gallery: media messages tab in channel (use MongoDB `idx_channel_media` index). | Guna | To Do | P1 | sprint-6;media;frontend | 16 | Epic
Sprint 6 ? Email Integration (Transactional via Resend) | SP6-03 | - Configure Resend API key and sender email. - Implement email templates: welcome, email-verification, password-reset. - Update auth endpoints to call Resend: - `POST /auth/signup` → send welcome email. - `POST /auth/verify-email` → on click, send confirmation email. - `POST /auth/forgot-password` → send reset link email. - Implement email unsubscribe link (optional for MVP). | Guna | To Do | P1 | sprint-6;email;resend | 14 | Epic
Sprint 6 ? n8n Webhooks & Automations | SP6-04 | - Deploy n8n instance (or use cloud). - Implement server webhooks: `POST /webhooks/n8n/message-created`, `POST /webhooks/n8n/user-signed-up`. - Implement webhook enqueue (Redis queue or in-memory): ack 202 immediately, process async. - Implement webhook retry logic: exponential backoff, max 5 retries, dead-letter queue on failure. - Implement HMAC-SHA256 webhook signing: include `X-Signature` header, n8n verifies. - Create n8n flow: trigger on message webhook → extract sentiment (call OpenAI or Hugging Face API) → store tag in MongoDB message. - Create n8n flow: trigger on user signup → log to Google Sheets or Slack (optional). - Implement monitoring: log webhook events, latencies, failures. | Guna | To Do | P1 | sprint-6;webhooks;n8n | 16 | Epic
Sprint 6 ? Media Processing (Optional MVP+) | SP6-05 | - Install `sharp` for image optimization: resize, convert to WebP. - Implement async media job: after upload, create thumbnail (360w) and preview (1080w). - Store processed files in S3 with optimized CDN paths. - Update MongoDB message: store both original + thumbnail URLs. | Guna | To Do | P1 | sprint-6;media;processing | 8 | Epic
Sprint 6 ? Testing | SP6-06 | - Unit tests: presigned URL generation, S3 key formatting. - Integration tests: upload file to S3, attach to message, verify URL persists in MongoDB. - Email tests: verify Resend receives correct payload, simulate bounce/unsubscribe. - Webhook tests: send webhook to n8n, verify signature validation, retry on failure. - User selects image, sees upload progress, sends message with attachment. - Message displays image thumbnail with zoom-on-click preview. - Verification email sent to user on signup; user clicks link, account activates. - n8n receives webhook on new message; sentiment tag appears in message history. - Upload fails gracefully: user sees error toast, can retry. - Webhook fails: server logs error, retries with backoff, eventually succeeds. | Guna | To Do | P1 | sprint-6;testing | 20 | Epic

## Sprint 7
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 7 ? Error Tracking & Observability | SP7-01 | - Integrate Sentry: install SDK, configure DSN, enable error capture on both backend + frontend. - Implement custom breadcrumbs: log socket events, API calls, database queries. - Implement performance monitoring: mark critical paths (send message, fetch history, auth). - Set up alerts: critical errors (5xx, auth failures, database connection loss). - Implement health check aggregator: `GET /health` returns { postgres, mongodb, redis } with latencies. - Add request/response logging middleware: log endpoint, status, latency, user_id. | Guna | To Do | P1 | sprint-7;observability;sentry | 12 | Epic
Sprint 7 ? Database & Connection Tuning | SP7-02 | - Tune Prisma connection pool: set min/max based on server threads (default 5/10). - Tune MongoDB connection pool: set maxPoolSize (default 100, monitor connection count). - Tune Redis connection backoff: implement exponential backoff for reconnects. - Implement connection timeout middleware: cancel slow queries after 10s (configurable). - Monitor: active connections, query latencies (P50, P95, P99). - Run load test: 100 concurrent users, measure DB connection saturation. | Guna | To Do | P1 | sprint-7;performance;database | 12 | Epic
Sprint 7 ? Cold-Start Mitigations | SP7-03 | - Implement scheduled ping jobs: hit `/health` every 5 min to keep Render container warm. - Implement connection keepalive: periodically query each database to prevent timeout. - Implement pre-warmed connection pools on server startup. - Measure and log cold-start latency on deploy. | Guna | To Do | P1 | sprint-7;performance;cold-start | 8 | Epic
Sprint 7 ? Security Hardening | SP7-04 | - Implement HMAC-SHA256 webhook signature verification on all n8n webhooks. - Implement signed S3 URLs with TTL (10 min for upload, 24h for download). - Implement rate-limit headers: return X-RateLimit-\* on all endpoints. - Implement input sanitization: SQL injection, XSS, command injection tests. - Implement CSRF protection (if needed for forms). - Implement ACL checks: verify user is channel member before responding with messages. - Enable HTTPS everywhere, enforce HSTS header. - Review all user inputs: validate length, type, format with Zod before DB insert. | Guna | To Do | P1 | sprint-7;security;hardening | 16 | Epic
Sprint 7 ? E2E & Load Testing | SP7-05 | - Create Playwright E2E test suite: signup → verify → login → create channel → send message → edit/delete → logout. - Create load test: 100 concurrent users, each sends 10 messages/min for 10 min. - Measure: response latencies, database query times, error rates, memory consumption. - Run load test against staging environment before launch. - Create smoke test: basic happy path (login → send → logout) runs before every deploy. | Guna | To Do | P1 | sprint-7;testing;e2e | 10 | Epic
Sprint 7 ? Monitoring & Alerts | SP7-06 | - Set up Upstash Redis dashboard monitoring: key count, memory, hit rates. - Set up MongoDB Atlas monitoring: connection count, query latency, storage. - Set up PostgreSQL monitoring: active connections, query cache hit ratio. - Set up alerts: database down, error rate >1%, response time P95 >1s, memory >80%. - Create runbook: escalation procedures, on-call contacts. | Guna | To Do | P1 | sprint-7;monitoring;alerts | 10 | Epic
Sprint 7 ? Testing | SP7-07 | - Unit tests: all middleware, utility functions, validators. - Integration tests: full flows (auth, send, edit, delete, reactions). - Security tests: attempt SQL injection, XSS, CSRF — all should fail gracefully. - Load tests: measure latency under 100, 500, 1000 concurrent users. - Errors are captured in Sentry with full stack traces + context. - Health check returns 200 with all services green. - Load test sustains 100 concurrent users with <500ms P95 latency. - Cold-start latency <2s (on first request after deploy). - All rate limits enforced; requests over limit get 429. - Signed webhook requests pass verification; tampered requests fail 401. - E2E test suite passes 100% on staging before deploy. | Guna | To Do | P1 | sprint-7;testing | 22 | Epic

## Sprint 8
Task Name * | Task ID | Description content | Task assignee | Status | Priority | Tags | Time Estimate | Task Type
Sprint 8 ? Staging Environment | SP8-01 | - Create staging environment: separate PostgreSQL, MongoDB, Redis, S3 buckets. - Copy production-like env vars to staging (except real API keys — use test credentials). - Deploy backend to staging (Render, Railway, or similar). - Deploy frontend to staging (Vercel, Netlify). - Configure staging domain: e.g., `staging.vibechat.dev`. - Enable SSL certificate for staging domain. | Guna | To Do | P1 | sprint-8;staging | 12 | Epic
Sprint 8 ? E2E Testing & QA | SP8-02 | - Run full E2E test suite on staging (Playwright, Cypress, or manual). - Test flows: signup → verify → login → create DM → send message → edit/delete → logout. - Test group flows: create group → add members → send message → see presence. - Test media: upload image → verify thumbnail shows → edit caption → delete. - Test realtime: 2 browsers, verify message appears in real-time. - Test presence: log out one user, verify offline in other user's presence list. - Test error scenarios: network failure, invalid token, rate limit exceeded. - QA sign-off: all test cases pass. | Guna | To Do | P1 | sprint-8;qa;e2e | 16 | Epic
Sprint 8 ? Performance & Load Testing (Staging) | SP8-03 | - Run load test on staging: 100 concurrent users, 10 msg/min for 30 min. - Verify: no errors, latencies stable, no DB connection leaks. - Verify: Sentry error rate <0.1%, no critical alerts. - Measure: cost per request (API, database, storage), estimate production cost. | Guna | To Do | P1 | sprint-8;performance;staging | 8 | Epic
Sprint 8 ? Security Review & Compliance | SP8-04 | - Security audit: OWASP Top 10 checklist. - Privacy: verify no PII in logs, Sentry, or cache. - Terms of Service: draft if needed (defer detailed legal review to post-launch). - Data retention: implement cleanup jobs (e.g., delete verified-but-unused accounts after 30 days). | Guna | To Do | P1 | sprint-8;security;compliance | 8 | Epic
Sprint 8 ? Launch Checklist | SP8-05 | - DNS: configure production domain, verify CNAME/A records. - SSL certificate: ensure valid, set auto-renewal. - Environment variables: all production secrets provisioned. - Database backups: enable automated daily backups + point-in-time recovery. - Monitoring & alerts: all dashboards, alerts, and runbooks ready. - Incident response: on-call schedule, escalation contact, communication channels. - Onboarding docs: README, setup guide, API docs (Swagger / Postman collection). - Announcement: prepare launch post, social media, beta user email. | Guna | To Do | P1 | sprint-8;launch | 16 | Epic
Sprint 8 ? Production Deployment | SP8-06 | - Deploy backend to production (same infra as staging, separate secrets). - Deploy frontend to production. - Run smoke test on production: verify `/health` returns 200, login works. - Monitor error rate & latencies for 1 hour post-deploy. - Monitor cost: verify spending matches estimates. - Announce launch: send email to beta testers, post on social media. | Guna | To Do | P1 | sprint-8;deployment;production | 12 | Epic
Sprint 8 ? Post-Launch Tasks & Deferred Backlog | SP8-07 | - Collect user feedback: in-app survey, Discord, email. - Monitor analytics: sign-ups, DAU, message volume, error rates. - Create deferred features backlog for Sprint 9+: - End-to-end encryption (E2EE): implement Signal Protocol with `one_time_prekeys`. - Full-text search: implement MongoDB Atlas Search on messages. - Message threading: replies group under parent message. - Voice/video calls: integrate Twilio or Daily.dev. - Read-only channels / announcements: admin-only send. - Group permissions: roles (admin, moderator, member) with ACL. - Custom emoji / emoji reactions: expand from 4 default emoji. - User mentions (@name) + notification: push notification when mentioned. - Message forwarding: send message to another channel. - Typing indicator improvements: show % similarity to avoid spam. - User profile: bio, avatar, status message. - Block / report user: harassment prevention. - Giphy / Tenor integration: GIF picker in message input. | Guna | To Do | P1 | sprint-8;post-launch;backlog | 32 | Epic
Sprint 8 ? Testing & Monitoring | SP8-08 | - Integration test: production smoke test (login → send → logout). - Monitoring: daily dashboard review, alert response SLA <15 min. - Staging passes all E2E tests (100% pass rate). - Load test on staging: 100 users, no errors, P95 <500ms. - Production deployment succeeds, smoke test passes. - Error rate <0.1%, latency P95 <500ms on production (1h post-deploy). - Launch announcement sent, beta users can sign up and use app. - Monitoring + alerts active, on-call rotation established. - Post-launch backlog documented and prioritized. | Guna | To Do | P1 | sprint-8;testing;monitoring | 18 | Epic